## Sheet1
Bugs |  | Functionality |  |  |  | UI
Where | Issue | Where | Issue | Solution |  | Where | Issue | Solution
Project editor (summary) | Double clicking the project summary is not calling the editor for new projects. (works with existing) | System (graphical editor) | No default system which could lead to inconsistencies in naming (system name in text editor might be different to system name in graphical editor) | Default parent system to that defined in text editor (as with bowtie) |  | Tree | Cannot right click to start new project | Allow a right click - new on project to begin a new project | The “Projects” node (like the one at the top of each individual project) has no context to allow the application to decide what it is that the user wanted to create. Everything else does. This would require more of a rewrite of how the tree works than we have time for.
System editor | Error message when making a second save of the system definition. Note – no changes have been made to ‘Prescribing System’ component. | Care Setting editor | Cannot create a hierarchy for care settings | Arrange in tree so parent/child relationship is clear | More of a tree rewrite than we have time for. | Descripton boxes (all editors) | When using a laptop, font for description is different to rest of editor | consistant font
Care Process (graphical editor) | Adding an additional step to the flow diagram adds it to the list in the text editor. Step is retained in the list in the text editor even when the step is deleted in the graphical editor | Details (from menu) | only have a details option for care process activity | Right click on any icon and retrieve a details page. Combine details and links on one editor. (Also features when having to detail cause/control/effect etc - have to come out and open another editor) |  | System (Graphical editor) | Extra clicks needed to label system and function icons | Blank field when added to the diagram, ready to type straight on. | That means creating the object with editing pre-selected, which means understanding more of the innards of the graph editor than we have time to do.
Bowtie (graphical editor) | Error message to say "The diagram has a broken link and has not been saved" When checking the diagram there do not appear to be any broken links. Close the editor but then unable to recall bowtie or create new one. Deleted hazard to start again but unable to create with the same name as the deleted. Try to create a new hazard with a different name but get same error with any causes etc. | Links (care process activity step) | Drop down box does not reflect tabs view | Match relationships. Links drop down should be same as view tabs. |  | Care Setting editor | Blank parent care setting | Detault to N/A
|  | Links (care process activity step) | Incorrect relationship semantics | Need to link Activity to Care Process (A) Care Setting (M), Hazard (M), Role (M) Cause (M) Control (M) Function (M) System (A through hierarchical system editor) |  | Role | No value to 'category' data item | Remove category field
|  | Overall | Nowhere for user to go for instant help on a particular task | Add 'tips' button under 'i' icon for *each* field/group | Use tool tips instead. Text needed. | Role (links) | Data in comments field retained so can have duplicate info saved | Once info is saved, clear all fields
|  | Function (graphical editor) | No editor call when right click - links | (look into 'all in one' editor) Have the ability to link functions |  | Care Process | No value to 'version' data item | Remove version field
|  | Overall - links | Check relationship semantics and linking ability |  |  | Links (care process activity step) | Unintuitive use of tabs | Repostion links button to above tabs viewer and add a title to the view: View links
|  | Overall - links | Saves duplicate link and unable to delete | Delete incorrect link from table when saved in error |  | Control editor | Edit drop down fields | Remove 'other' remove 'test control' default to select and enable free text
[6 empty] | Control editor | incorrect naming of data fields | State = 'to be implemented', 'implemented' and 'impremented and verified' Condition = (change to type) = 'existing' and 'additional'
[6 empty] | Effect editor | No value to data field | Remove 'type' of effect
[6 empty] | Issues | Nowhere to add issue number | Add data field (freetext): 'Reference number'
[6 empty] | Project editor (summary) | Text view cut off (text: surface large) | Expand box so full field names are shown
[6 empty] | Care Process Editor | Not easy to view list of Process steps | Make process steps box bigger and description box shorter